## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2024-12-03
Group Number |  | 23
Participant 1 |  | Dervisefendic Armin
Participant 2 |  | Erdem Mehdi
Participant 3 |  | Lamthi Mateo
Participant 4 |  | Puka Benjamin
Participant 5 |  | Zehinovic Aldin
Mentor |  | Rohatsch Lukas
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Angefangen mit dem UI Design; Prototyp in Figma | 2.5 | 2 | -0.5 | 1 |  | Mehdi Erdem, Dervisefendic, Zehinovic
2 | Architecture design für das central node | 2 | 1.5 | -0.5 | 1 |  | Mehdi Erdem
3 | Recherche für das Umsetzung des central node (spring boot, docker) | 2 | 1.5 | -0.5 | 1 |  | Mehdi Erdem
4 | pgadmin, tabellen erstellt | 2 | 1 | -1 | 1 |  | Mehdi Erdem, Dervisefendic, Zehinovic
|  |  |  | -2.5 | 4 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol