## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2024-12-17
Group Number |  | 23
Participant 1 |  | Dervisefendic Armin
Participant 2 |  | Erdem Mehdi
Participant 3 |  | Lamthi Mateo
Participant 4 |  | Puka Benjamin
Participant 5 |  | Zehinovic Aldin
Mentor |  | Rohatsch Lukas
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Backend Setup (Spring Boot) | 2 | 2 | 0 | 1 |  | Mehdi, Dervisefendic, Zehinovic
2 | Frontend Setuo (React.js) | 2 | 3 | 1 | 1 |  | Mehdi, Dervisefendic, Zehinovic
3 | Database | 3 | 3 | 0 | 1 |  | Mehdi
4 | Figma (Refining the prototype) | 2 | 3 | 1 | 1 |  | Zehinovic, Dervisefendic
4 |  |  |  | 2 | 4 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol